## Slide 1: NPI Sourcing Process 2.0 Stage Reviews January 8, 2024

## Slide 2: NPI Sourcing Process 2.0 Overview
Project Execution
by OnePlan
Execution
Product Release
Post Market Review
Supplier Evaluation
Potential Suppliers
Product Request
GF-0056, Agreements,
Artwork, Set up
Launch PO, Marketing Material & Launch
Business Reviews
Supplier Quote Analysis
Preliminary Evaluation
BU
QARA
Sourcing
R&D
Finance
SC
Team Engagement
  Post Market
Review
Business Proposal
GF-0011
R&D Testing
Quality Audit
Business Case
Project Initiation
by OnePlan
I
GF-0056
Supplier Selection
Launch PO
GF-0011 Approved
Supplier Screen
II
NPI Committee Meeting
Monthly Meeting – Every 3rd Week
III
Stage 1
Stage 2
Stage 3
Stage 4
Stage 5
Stage 6
Notes: Change highlight: Instead of sending it to Sourcing only, it will now go to QARA + Sourcing. (Risk Assessment & Supplier Requirements – Benefit – Control Tower for Sourcing Portfolio)

## Slide 3
What’s Changed & What’s Next
Stage Review Process
Product Request
Potential Suppliers
Supplier Evaluation
Execution
Product Request GF-0011 must be sent for review & get email approval from Mike, Peter, Bryan & Claudia before routing in GG.
Sourcing Lead to again present the project progress to NPI Committee in Monthly Meeting.
Sourcing Lead must provide Project names & stage they want to present by Week 1 Friday.
Sourcing Lead to again present the project progress to NPI Committee in Monthly Meeting.
Sourcing Lead must provide Project names & stage they want to present by Week 1 Friday.
Sourcing Lead to present the project progress to NPI Committee in Monthly Meeting.
Sourcing Lead must provide Project names & stage they want to present by Week 1 Friday.
Note:
First Meeting will be held on Jan 22nd, 2025, Wednesday.
Please share project names and stage you want to present by Monday 13th by sending an email to Gaurav & Claudia.
All Sourcing Projects Stage 2 Onwards must be presented to NPI Committee Meeting before moving onto next stage.
Stage 1
Stage 2
Stage 3
Stage 4
Notes: Change highlight: Instead of sending it to Sourcing only, it will now go to QARA+Sourcing. (Risk Assessment & Supplier Requirements – Benefit – Control Tower for Sourcing Portfolio

## Slide 4
Supplier Evaluation
Potential Suppliers
Product Request
Execution
Stage | What | How | Who
Stage 1 Product Request | Business Case (Target Revenue & GM) QARA Risk Assessment Outcome: (Provided by Sourcing Director) Sourcing Sponsor Assignment OnePlan Project Number | 1. Email (1 page Business case) To: Peter, Bryan, Claudia, Mike Xie 2. After email approval, route GF-0011 | Initiator: Business Unit Email Approvers: Peter, Mike, Claudia, Bryan Sponsor: Sourcing Director Sourcing Lead: Assigned Sourcing Manager
Stage 2 Potential Suppliers | Identified potential supplier(s) Quote Analysis Samples review by BU Business Case (Revenue & GM) Outside China suppliers explored/evaluated | NPI Committee Meeting: 1. Business Case Update 2. One-Slide project summary | Lead: Sourcing Lead
Stage 3 Supplier Evaluation | R&D Test Results Patent Review (If needed) Quality Audit & CAPA Plan Business Case (Revenue & GM): Final | NPI Committee Meeting: One-Slide project summary | Lead: Sourcing Lead
Stage 4 Execution with Selected Supplier | GF-0056 initiated and completed Artwork Supply Agreements All project tasks initiated and completed Outcome: Launch PO Approval | NPI Committee Meeting: One-Slide project summary | Lead: Business Unit
Stage Review Process 2.0
Notes: Change highlight: Instead of sending it to Sourcing only, it will now go to QARA+Sourcing. (Risk Assessment & Supplier Requirements – Benefit – Control Tower for Sourcing Portfolio

## Slide 5: NPI Committee Meeting
Week 1:
Sourcing Lead send an email to Gaurav & Claudia with project and stage they want to present.
Week 2:
Claudia & Gaurav provides agenda.
Week 4:
Claudia & Gaurav to provide Meeting Notes & Action
Execution Framework
Action Planning & Implementation
Visibility & Alignment
Closing
Post – Call Action
Pre-Call Planning
Prepare
Chart: 
| Business Unit | QARA | Sourcing
Sales | 1 | 1 | 1
Priority
Alignment
Visibility
Week 2
Executive Dashboard
Stakeholder Brief
Week 1
Agenda Proposal
(Sourcing Lead)
Week 4
Post Call Action
Week 3
Meeting
Week 3:
Meeting – Every 3rd week of the month

## Slide 6: Stage 2 Template - Potential Suppliers
Company Details:
Manufacturing Site
Company Revenue
Contract Type
Notes
Sourcing Lead:
Date:
Quote Details
Include the unit cos
MOQ
Lead time
BU Samples Review:
Potential
Supplier
II
Note: One slide per supplier may be presented at this stage
Business case
Include Countries
Revenue
Unit cost
Freight cost
GM%
Outside China Suppliers Evaluated
Notes: GF-0011 should be filled only when there is a confirmed supplier. Check – GF-0011, Procedure PPT.

## Slide 7: Stage 3 Template - Suppliers Selection
Company Details
Manufacturing Site
Company Revenue
Contract Type
Notes
Sourcing Lead:
Date:
Quote Details
Include the unit cost
MOQ
Lead time
Samples Review
Business case
Include Countries
Revenue
Unit cost
Freight cost
GM%
R&D Testing and patent review results
Quality Audit results
Supplier Selection
III
Notes: GF-0011 should be filled only when there is a confirmed supplier. Check – GF-0011, Procedure PPT.

## Slide 8: Stage 4 Template – Launch Order approval
Item | Status | RAG
PR Number | Not ready. PM is finalizing on details | Red
GF-0056 Status | Done | Green
R&D Testing | No special testing. Patent analysis done | Green
Quality Audit | Not yet, was aligned may have audit after launch order | Yellow
Supply Agreement | Done | Green
Labeling | Lack of Customer confirmation on IFU | Red
Regulatory Registration | Done | Green
Supplier Details
Manufacturing Site: Zhenjiang POCTech Co., Ltd for CGM and Yuwell medical for BGM+Thermometer etc.
Contract Type: SPP project with supply agreement
Markets: Global
Notes: Yuwell owns 100% of POCTech so agreement signed with Yuwell.
Sourcing Lead
Last Updated:
Launch Order details:
Launch Order
Approval
IV
Product Details
Manufacturing Site: Zhejiang POCTech Co., Ltd
Contract Type: SPP project, Co-brand
Markets: Swiss only
Payment:30%+70% before shipment
MOQ:5000pieces for OEM
Leadtime: 60days
Price condition:
1500USD for plate cost
15USD for transmitter but cost will be waived if the volume of sensors hit 15,000 before 2025 July.
 | Delivery Dec. 2024 | Delivery April 2025
CT 3 sensors | 4280 (107 ca) | 4480 (112 ca)
CT 3 transmitters | 640 (16 ca) | 200 units (5 ca)
Production date to be printed on boxes | November or December | March or April
Notes: GF-0011 should be filled only when there is a confirmed supplier. Check – GF-0011, Procedure PPT.

## Slide 9: NPI Sourcing Process 2.0 Overview
Project Execution
by OnePlan
Execution
Product Release
Post Market Review
Supplier Evaluation
Potential Suppliers
Product Request
Agreements,
Supplier Setup,
PO
Marketing Material & Launch
Business Reviews
Supplier Quote Analysis
Preliminary Evaluation
BU
QARA
Sourcing
R&D
Finance
SC
Team Engagement
Post Market
Review
Business Proposal
GF-0011
R&D Testing
Quality Audit
Business Case
Project Initiation
By OnePlan
I
GF-0056
Supplier Selection
Launch PO
GF-0011 Approved
Supplier Screen
II
NPI Committee Meeting
Monthly Meeting
III
Notes: Change highlight: Instead of sending it to Sourcing only, it will now go to QARA + Sourcing. (Risk Assessment & Supplier Requirements – Benefit – Control Tower for Sourcing Portfolio